## Regression
REG ID | Scope | Related TCs | Status | Actual Result | Defect ID | Evidence | Date
REG-001 | Login | TC-AUTH-001/002 | Pass | Admin login lands dashboard (12-item nav) on current build |  | evidence/regression/REG-001-login.png | 2026-10-03
REG-002 | Logout | TC-AUTH-007 | Pass | Logout returns to /auth/login |  | evidence/smoke/TC-AUTH-007-after-logout.png | 2026-10-03
REG-003 | Dashboard | TC-DASH-001 | Pass | Dashboard + 12-item nav render on current build |  | evidence/regression/REG-003-dashboard.png | 2026-10-03
REG-004 | Employee search | TC-PIM-004/005 | Pass | E2091 ID search returns exactly 1 card on current build |  | evidence/smoke/TC-PIM-001-created-E2091.png | 2026-10-03
REG-005 | Create employee | TC-PIM-001 | Pass | E2094 (Regression Check) saved: "Successfully Saved" on current build |  | evidence/regression/REG-005-create-E2094.png | 2026-10-03
REG-006 | Edit employee | TC-PIM-007 | Pass | E2091 middle-name edit persists after reload ("Successfully Updated") |  | evidence/regression/REG-006-edit-E2091.png | 2026-10-03
REG-007 | Apply leave | TC-LEAVE-002 | Blocked | Entitlement precondition still unmet — no leave types with balance for qa_ess; cannot regress submit |  | evidence/smoke/TC-LEAVE-002-ess-apply-form.png | 2026-10-03
REG-008 | View leave | TC-LEAVE-004(view) | Pass | Leave list page renders on current build (0 rows — correct, no requests exist) |  | evidence/regression/REG-008-leave-list.png | 2026-10-03
REG-009 | Cancel leave | TC-LEAVE-009 | Blocked | No pending request exists (blocked submit upstream); nothing to cancel |  | evidence/smoke/TC-LEAVE-002-ess-apply-form.png; evidence/regression/REG-008-leave-list.png | 2026-10-03
REG-010 | Time action | TC-TIME-001/002 | Pass | ESS punch-in saves + record visible; punch-out saves — full cycle green on current build |  | evidence/regression/REG-010-punched-in.png; evidence/regression/REG-010-punched-out.png; evidence/regression/REG-010-my-records.png | 2026-10-03
REG-011 | Logout/session | TC-AUTH-008 | Pass | Post-logout direct /dashboard/index lands on /auth/login; no content exposed |  | evidence/regression/REG-011-session-guard.png | 2026-10-03