## Execution
TC ID | Status | Actual Result | Defect ID | Notes | Date | Env
TC-AUTH-001 | Pass | Login page HTTP 200/title OrangeHRM with username+password+Login; qa_admin login lands /dashboard/index <5s with admin user menu |  | evidence/smoke/TC-AUTH-001-login-page.png + TC-AUTH-002-admin-dashboard.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-002 | Fail | ESS login lands /dashboard/index with restricted 8-item nav (Leave/Time/My Info/Performance/Dashboard/Directory/Claim/Buzz); Admin+PIM+Recruitment+Maintenance absent. Expected text says "PIM/Leave visible" — PIM is correctly hidden for ESS; test-design wording needs correction, NOT an SUT defect. No BUG filed. |  | evidence/smoke/TC-AUTH-002-ess-dashboard.png; TEST-DESIGN issue flagged, Expected frozen per process | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-003 | Pass | Wrong password rejected; stays on /auth/login with "Invalid credentials" toast; no session |  | evidence/smoke/TC-AUTH-003-invalid-password.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-004 | Pass | Unknown username rejected with generic "Invalid credentials" (same as wrong password — no account enumeration); stays on login, no session |  | evidence/smoke/TC-AUTH-004-unknown-user.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-005 | Pass | Empty username+password rejected inline with "Required" x2; stays on login, no session |  | evidence/smoke/TC-AUTH-005-empty-credentials.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-006 | Pass | Whitespace-only credentials treated as empty: "Required" x2 shown; stays on login, no session |  | evidence/smoke/TC-AUTH-006-whitespace-credentials.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-007 | Pass | Logout via user menu returns to /auth/login |  | evidence/smoke/TC-AUTH-007-after-logout.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-AUTH-008 | Pass | Browser Back + direct /dashboard/index after logout both land on /auth/login; no authenticated content or action possible |  | evidence/smoke/TC-AUTH-008-back-button.png + TC-DASH-004-direct-url-after-logout.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-DASH-001 | Pass | Admin dashboard loads with 12-item nav (Admin/PIM/Leave/Time/Recruitment/My Info/Performance/Dashboard/Directory/Maintenance/Claim/Buzz); ESS dashboard loads with 8-item restricted nav |  | evidence/smoke/TC-DASH-001-dashboard-load.png + TC-AUTH-002-*-dashboard.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-DASH-002 | Pass | PIM/Leave/Time/Recruitment nav targets each land on matching module (h6 PIM/Leave/Time+Timesheets/Recruitment) |  | evidence/smoke/TC-DASH-002-nav-recruitment.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-DASH-003 | Not Run
TC-DASH-004 | Pass | Unauthenticated /dashboard/index redirects to /auth/login; no dashboard content exposed |  | evidence/smoke/TC-DASH-004-direct-url-after-logout.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-001 | Pass | E2001 (Aarav Sharma, DOB 1990-01-15 per valid_employee.csv) saved ("Successfully Saved"), found by ID search (1 card), DOB persists after refresh. Conforming rerun 2026-10-03; exploratory E2091 probe retained as supporting evidence. |  | evidence/smoke/TC-PIM-001-E2001-saved.png + TC-PIM-001-E2001-in-list.png + TC-PIM-007-E2001-detail.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-002 | Pass | Empty-required blocked inline ("Required" x2, stays on form); duplicate E2001 blocked ("Employee Id already exists"); ID search confirms still exactly 1 E2001 record — no silent save, no duplicate. Conforming rerun 2026-10-03. |  | evidence/smoke/TC-PIM-002-E2001-duplicate.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-003 | Fail | Assumed 50-char max is wrong: 50-char rejected, and true limit observed at 30 ("Should not exceed 30 characters"); 30-char accepted+saved+retrievable (E2092), 31-char rejected. App validation correct and consistent — test-design assumption needs correction, NOT an SUT defect. No BUG filed. |  | evidence/smoke/TC-PIM-003-true-boundary-30-31.png; Expected frozen per process | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-004 | Pass | Name autocomplete suggests Aarav; select+Search returns exactly 1 card (E2001 Aarav Sharma); Reset restores full list (6 cards). Conforming rerun 2026-10-03 with search_test_data.csv 'Aarav'. |  | evidence/smoke/TC-PIM-004-Aarav-search.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-005 | Pass | Name query 'ZzzNoMatch' returns 0 cards with 'No Records Found' empty state — no stale rows. Conforming rerun 2026-10-03; free text IS submitted as a filter (earlier select-only theory disproven). |  | evidence/smoke/TC-PIM-005-ZzzNoMatch.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-006 | Not Run
TC-PIM-007 | Pass | E2001 detail shows stored creation data (Aarav Sharma, E2001, DOB 1990-01-15 persists after save+refresh). Conforming rerun 2026-10-03. |  | evidence/smoke/TC-PIM-007-E2001-detail.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-PIM-008 | Not Run
TC-PIM-009 | Not Run
TC-PIM-010 | Not Run
TC-PROF-001 | Not Run
TC-PROF-002 | Not Run
TC-PROF-003 | Not Run
TC-PROF-004 | Not Run
TC-PROF-005 | Not Run
TC-PROF-006 | Not Run
TC-LEAVE-001 | Blocked | ESS Apply Leave renders "No Leave Types with Leave Balance" — submission preconditions (leave type + entitlement/balance for qa_ess) not configured in this cycle; cannot assert submit behaviour |  | evidence/smoke/TC-LEAVE-002-ess-apply-form.png; precondition: provision leave entitlement then re-execute | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-LEAVE-002 | Blocked | Same entitlement precondition as TC-LEAVE-001; half-day submit not attemptable |  | evidence/smoke/TC-LEAVE-002-ess-apply-form.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-LEAVE-003 | Not Run
TC-LEAVE-004 | Not Run
TC-LEAVE-005 | Not Run
TC-LEAVE-006 | Not Run
TC-LEAVE-007 | Not Run
TC-LEAVE-008 | Not Run
TC-LEAVE-009 | Not Run
TC-LEAVE-010 | Not Run
TC-LEAVE-011 | Not Run
TC-LEAVE-012 | Not Run
TC-TIME-001 | Pass | ESS punch-in saves ("Successfully Saved") and creates visible attendance record with timestamp in My Records (1 row) |  | evidence/regression/REG-010-punched-in.png + REG-010-my-records.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-TIME-002 | Pass | ESS punch-out saves ("Successfully Saved"), completing the in/out cycle the same day |  | evidence/regression/REG-010-punched-out.png | 2026-10-03 | Ubuntu 24.04.5 LTS; Firefox 155.0 (Playwright firefox-1543); OrangeHRM 5.8.1 pinned (5eb278ac); 1920x1080
TC-TIME-003 | Not Run
TC-TIME-004 | Not Run
TC-TIME-005 | Not Run
TC-REC-001 | Not Run
TC-REC-002 | Not Run
TC-REC-003 | Not Run
TC-REC-004 | Not Run
TC-REP-001 | Not Run
TC-REP-002 | Not Run
TC-REP-003 | Not Run
TC-UI-001 | Not Run
TC-COMP-001 | Not Run